## SBS Estimate
|  | Job Name: | Salthill
|  | Type: | 2 Ply SBS Stripping Torch
Roof System: 3182 ft2 - MD, 1/2" Dens, HPR Base, StressPly IV Plus Cap, Drainage,Re-Use Rubber Mat, Re-Use 1" + 2" XPS, Grass by Others
Quantity | Type | Descriptions | Price | Total
|  |  |  | 0 | 31.8 | SQS
100 | SHEETS | 1/2" DENSDECK PRIME | 36.5 | 3650
11 | BOX | INSUL-LOCK FOAM ADHESIVE | 880 | 9680
0
34 | ROLLS | HPR BASE (97 FT2) - FIELD | 538 | 18292
1 | PAILS | PRO-STOP FR PRIMER | 939 | 939
5 | ROLLS | SA BASE IV - STRIPPING (97 FT2) | 515 | 2575
7 |  |  |  | 0
44 | ROLLS | STRESSPLY IV PLUS CAP (75 FT2) - FIELD | 599 | 26356
6 | ROLLS | STRESSPLY IV PLUS CAP (75 FT2) - STRIPPING | 599 | 3594
0
11 | ROLLS | SOPRADRAIN 10-G (300 FT2) | 226.5 | 2491.5
0
285 | FEET | CANT | 2.5 | 712.5
29 | LENGTH | TERM BAR | 12.5 | 362.5
24 | ROLLS | FIRETAPE | 28 | 672
0
0
0
0
1 | BAGS | SEAL-TITE SINGLE PART STPE PITCH POCKET (4) | 508 | 508
| CASE | TUFF STUFF MS SILICONE SEALANT (24 / CASE) | 790 | 0
| EACH | DRAINS C/W U-FLOW | 550 | 0
3 | PAILS | GARLA-FLEX (30 FT2 / PL) - VERTICAL SEAMS | 542 | 1626
1 | ROLLS | 6" GARMESH - 150' - VERTICAL SEAMS | 105 | 105
0
0
0
10 | SHEETS | 24 GAUGE PREFINISHED | 75 | 750
| SHEETS | 26 GAUGE GALV | 50 | 0
1 | LOADS | FREIGHT - MATERIALS | 1150 | 1150
31.8 | SQS | MISC | 30 | 954
74417.5
|  |  | SQS | ft2 | m2
|  |  | 31.8 | 23.4017 | 295.4322
LABOUR
Quantity | Days/Hours | Crew / Scope Description | Rate | Total | Productivity
1 | days | Set up (Roof Load) - 5 man | 2060 | 2060 | Man Hr | Per
2 | days | Demolition - Fence + Insulation + Rubber Mat Store | 2060 | 4120 | 0.33849 | m2
0.75 | days | Install Densdeck - Adh | 2060 | 1545 | 0.12693 | m2
0.5 | days | Install Firetape | 2060 | 1030 | 0.084622 | m2
1.25 | days | Torch Base | 2060 | 2575 | 0.21155 | m2
1.25 | days | Torch Cap | 2060 | 2575 | 0.21155 | m2
0.75 | days | Re-Install Insulation | 2060 | 1545 | 0.12693 | m2
0.5 | days | Re-Install Rubber Matt + Fencing | 2060 | 1030 | 0.084622 | m2
8 | days | Firewatch (2 men x 2 hrs each) | 175 | 1400
285 | feet | Metal Fabrication | 3.25 | 926.25 | 0.25863 | ln m
285 | feet | Metal Install | 4 | 1140 | 0.31832 | ln m
285 | feet | Carpentry (Cant) | 1.75 | 498.75 | 0.13926 | ln m
8 | sqs | MB Stripping | 350 | 2800 | 0.91441 | m2
|  | Supervision % | 6% | 1394.7 | 33.8519 | man hrs
| trips | travel / 3 men / round trip | 496 | 0 | Total Man Hours
|  | Overtime | 10% | 2463.97 |  | 598.051
SQS / DAY | 3.6971 |  | Net | 27103.67
|  | Overburden | 25% | 6775.9175 | Per ft2
|  |  | Total | 33879.5875 | 10.654
Miscellaneous
|  |  | Rate | Total
31.8 | SQS |  |  | 0
13 | Days | Truck & Fuel (10 Roofing / 3 Metal) | 150 | 1950
| Man Days | Room & Board (5 Men) | 110 | 0
6 | Hrs | Crane | 295 | 1770
2 | Loads | Dump + Rental Bin or Truck | 1150 | 2300
| L/S | 5 Year "Contractor" Warranty (3%) |  | 0
1 | L/S | Sub Trade - Panels (Addendum 3) | 15000 | 15000
1 | L/S | Sub Trade - Glazing (Addendum 4) | 5000 | 5000
31.8 | SQS | Safety Misc | 10 | 318
31.8 | SQS | TEC (Truck, Equipment, Communications) | 10 | 318
6 | UNITS | Propane (15 sqs / bottle / layer) (10 sqs - winter) | 115 | 690
1 | Month | P-Can + Fence | 950 | 950
| days |  | 1200 | 0
| 1000's | Bonding | 10 | 0
|  |  | TOTAL | 28296
|  |  | NET | 136593.0875 | % On Sale
|  | Profit | 138% | 46753.8308 | 25%
|  | Insurance | 2% | 3666.9384 | 58.8094
TOTAL SALE |  |  |  | 187013.8566 | Per ft2

## Job Codes
CODE | DESCRIPTION | AMOUNT
7080 M | Roofing Materials | 73267.5
1440 M | Freight Materials | 1150
7080 L | Roofing Labour | 30868.0281
1410 L | Metal Labour | 3011.5594
1210 O | Job Truck & Fuel | 1950
1425 O | Room & Board | 0
1280 E | Crane / Forklifts / Lifts | 1770
1150 O | Bins, Dumping & Disposal | 2300
1163 O | Roofing Warranty | 0
15000 S | Mechanical Sub | 15000
16000 S | Vacuum Sub | 5000
1140 E | Safety Equipment & Training | 318
1270 O | Consumables, Tools, Jobshacks | 1268
7095 O | Propane | 690
1120 O | Insurance | 3666.9384
| Profit | 46753.8308
99999 R | Revenue / Contract Amount | 187013.8566

## Schedule of Values
Trucraft Roofing (2005) Ltd.
Job Name: | Triovest
Schedule Of Values |  | Job# |  |  |  |  | 2015-01-31
Claim # 1
ORIGINAL CONTRACT VALUE: | 187013.8566 | Amount | % Complete | TOTAL CLAIM | PREV CLAIMS | THIS CLAIM | % To claim | Left to Claim
MATERIALS
Roofing |  | 89454.5153 | 0% | 0 | 0 | 0 | 100% | 89454.5153
Metal |  | 937.5015 | 0% | 0 | 0 | 0 | 100% | 937.5015
Freight |  | 1437.5023 | 0% | 0 | 0 | 0 | 100% | 1437.5023
LABOUR
Set-Up |  | 3753.0684 | 0% | 0 | 0 | 0 | 100% | 3753.0684
Demolition |  | 7506.1368 | 0% | 0 | 0 | 0 | 100% | 7506.1368
Install - Roofing |  | 27325.8905 | 0% | 0 | 0 | 0 | 100% | 27325.8905
Install - Metal |  | 3764.4551 | 0% | 0 | 0 | 0 | 100% | 3764.4551
GENERAL
Insurance |  | 7333.8767 | 0% | 0 | 0 | 0 | 100% | 7333.8767
Crane / Forklift / Zoom Boom |  | 1770 | 0% | 0 | 0 | 0 | 100% | 1770
Waste Disposal |  | 2300 | 0% | 0 | 0 | 0 | 100% | 2300
Fuel / Propane |  | 2640 | 0% | 0 | 0 | 0 | 100% | 2640
Vacuum |  | 6250.0098 | 0% | 0 | 0 | 0 | 100% | 6250.0098
Mechanical / Electrical |  | 18750.0294 | 0% | 0 | 0 | 0 | 100% | 18750.0294
Room and Board |  | 0 | 0% | 0 | 0 | 0 | 100% | 0
Security / Safety / Communications |  | 636 | 0% | 0 | 0 | 0 | 100% | 636
Warranty and Inspections |  | 0 | 0% | 0 | 0 | 0 | 100% | 0
Bonding |  | 0 | 0% | 0 | 0 | 0 | 100% | 0
Overhead |  | 13154.8709 | 0% | 0 | 0 | 0 | 100% | 13154.8709
Change Orders:
|  | 0 | 0% | 0 | 0 | 0 | 100% | 0
|  | 0 | 0% | 0 | 0 | 0 | 100% | 0
|  | 0 | 0% | 0 | 0 | 0 | 100% | 0
TOTAL CONTRACT VALUE |  | 187013.8566 |  | 0 | 0 | 0 |  | 187013.8566
Less holdback @ 10% |  | -18701.3857 |  | 0 | 0 | 0 |  | -18701.3857
Sub total |  | 168312.471 |  | 0 | 0 | 0 |  | 168312.471
GST @ 5% |  | 8415.6235 |  | 0 | 0 | 0 |  | 8415.6235
Total Claim |  | 176728.0945 | 0% | 0 | 0 | 0 | 100% | 176728.0945