| Tentative Schedule |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Royal Oak Park – Daycare. 2025 Roof Replacement RS 1.6.1 8650 – 112 Ave. N.W. |  |  |  |  |  |
| Job #17,771 |  |  |  |  |  |
| No. | 2025/26 Date/s: |  | Item: |  |  |
| 1. | December 3 |  | Set-up project; set-up compound & chute. |  |  |
| 2. | December 3 - 10 |  | Demo existing grass, metal flashings, wall panels & rubber pads. |  |  |
| 3. | December 10 |  | Load material. Please note: All material to be loaded with crane, before tenants open. |  |  |
| 4. | December 11 – 19 |  | Remove existing roof membrane, then install new DensDeck & first ply of membrane. |  |  |
| 5. | December 22 – 31 |  | Install second ply of membrane. |  |  |
| 6. | January 5 – 9 |  | Re-install panels. |  |  |
| 7. | January 8 – 15 |  | Install new flashing. |  |  |
| Please note: All dates are weather dependent. We will update schedule if needed. |  |  |  |  |  |
| as of November 14, 2025 |  |  |  |  |  |